## Terms and Conditions
INFORMATION & INSTRUCTIONS FOR BIDDERS FOR E-TENDERING — pages: 4, 5, 6, 7, 8
No. | Text
1. | The work is estimated to cost Rs.58,63,632.00 this estimate, however, is given merely as a rough guide.
2. | Intending bidders is eligible to submit the bid provided he has definite proof from the appropriate authority, which shall be to the satisfaction of the competent authority, of having satisfactorily completed similar works of magnitude specified below: - Should have satisfactorily completed the works as mentioned below during the last 7 years ending last day of the month previous to the one in which tenders are invited. (For this purpose, cost of work shall mean gross value of the completed workincluding cost of material supplied by the Government/Client but excluding those supplied free of cost.) Three similar works each costing not less than 15.63 Lacs, OR Two similar works each costing not less than 23.45 Lacs, OR One similar works each costing not less than 31.27 Lacs, Similar work shall mean 'Maintenance of Fire Alarm System" Note-1: The cost of the work should be certified by an Officer not below the rank of Executive Engineer/ Project Manager or equivalent.
3. | This information and instructions for bidders posted on website shall form part of bid document.
4. | The bid document consisting of Plans, Specifications, Schedule of quantities of various types of items to be executed and the set of terms and conditions of the contract to be complied with and other Necessary documents can be seen and downloaded from website https://etender.cpwd.gov.in or www.cpwd.gov.in free of cost.
5. | But the bid can only be submitted after deposition of original EMD either in the office of Executive Engineer inviting bids or division office of any Executive Engineer, CPWD within the period of bid submission and uploading the mandatory scanned documents such as Insurance Surety Bonds, Account Payee Demand draft or Bankers Cheque or Fixed Deposit Receipts or/and Bank Guarantee (for balance amount as prescribed) from any of the Commercial Bank towards EMD in favour of Executive Engineer as mentioned in NIT, receipt for deposition of original EMD to division office of any Executive Engineer (including NIT issuing EE/ AE), CPWD and other documents as specified.
6. | Those contractors not registered or have not updated their profile on the website mentioned above, are required to get registered / update their profile beforehand. The necessary training materials including the videos with step-to-step process are available on download section of https://etender.cpwd.gov.in
7. | The intending bidder must have valid class-III digital signature certificate with encryption key (combo type) to perform any operation/ transaction on the e tendering portal/web site and the bidder should download and install the e-Messenger on their system as per instructions available on download section of https://etender.cpwd.gov.in.
8. | On opening date, the contractor can login and see the bid opening process. After opening of bids, he will receive the competitor bid sheets.
9. | Contractor can upload documents in the form of JPG format and PDF format.
10. | Certificate of Financial Turn over: At the time of submission of bid contractor may upload Affidavit/Certificate from CA mentioning Financial Turnover of last 7 years or for the period as specified in the bid document and further details if required may be asked from the contractor after opening of technical bids. There is no need to upload entire voluminous balance sheet.
11. | Contractor must ensure to quote rate of each item. The column meant for quoting rate in figures appears in yellow colour and the moment rate is entered; it turns sky blue. In addition to this, while selecting any of the cells a warning appears that if any cell is left blank the same shall be treated as "0". Therefore, if any cell is left blank and no rate is quoted by the bidder, rate of such item shall be treated as "0" (Zero). However, if a tenderer quotes nil rates against each item in item rate tender or does not quote any percentage above/below on the total amount of the tender or any section/sub head in percentage rate tender, the tender shall be treated as invalid and will not be considered as lowest tenderer.
12. | The Technical Bid/ Eligibility bid shall be opened first on due date and time as mentioned above. The time and date of opening of financial bid of Bidders qualifying the Technical cum Eligibility Bid shall be uploaded on website only at later date. The department reserves the right to reject any prospective application without assigning any reason and to restrict the list of qualified contractors to any number deemed suitable by it, if too many bids are received satisfying the laid down criterion. The contractor submitting the bid should read the schedule of quantities, Special conditions, additional conditions, particular specifications and other terms and conditions given in the NIT and drawings. The bidder should also read the General Conditions of Contract Maintenance Works 2023 with all correction slips issued up to the last date for submission of bid, which is available as Government of India Publication. However, provisions included in the bid document shall prevail over the provisions contained in the standard form. The set of drawings and NIT will be available with the Executive Engineer (E), President Estate Electrical Division, CPWD, New Delhi-110004. The contractor should also visit the site of work and acquaint himself with the site conditions before tendering. The following conditions, which already form part of the tender conditions, are specially brought to his notice for compliance while filling the tender. They are requested to comply with the following instructions.
13. | Tenders with any condition including that of conditional rebates shall be rejected. Such tenders shall not be entered in the tender opening register at the time of opening of tender. Applicants are advised to keep visiting the https://etender.cpwd.gov.in.web-sites from time to time (till the deadline for bid submission) for any updates in respect of the tender documents, if any. Failure to do so shall not absolve the applicant of his liabilities to submit the applications complete in all respects including updates thereof, if any. An incomplete application may be liable for rejection. If any information furnished by the applicant is found to be incorrect at a later stage, he shall be liable to be debarred from tendering/taking up of works in CPWD. The department reserves the right to verify the particulars furnished by the applicant independently. Any dispute arising out of this tender including dispute related to encashment of any Bank Guarantee/ FDR etc. shall be subject to the jurisdiction of courts at New Delhi only.
14. | List of Documents to be scanned and uploaded within the period of bid submission:
NIT No. | 41/EE/E/PEED/2026-2027
Name of Work | RMO Fire Alarm & Fire Fighting System at Rashtrapati Bhavan, New Delhi. (SH: - Operation & Comprehensive maintenance of Fire Alarm system & Fire Fighting System at different locations in Rashtrapati Bhavan).
Address of site | Inside the campus of Rashtrapati Bhavan, New Delhi.
Estimated cost put to bid | Rs. 58,63,632.00
Earnest Money | Rs. 1,17,273.00
Period of Completion | 12 Months
Last time & date of submission of bid, other documents as specification Notice Inviting e- Tender. | 13/08/2026 upto 15:00 Hrs.
Eligiblity Bid Opening date | 13/08/2026 upto15:30 Hrs.
Submission of hard copies of EMD. | 13/08/2026 upto15:00 Hrs.
Hard copy of Enlistment order, Affidavit, Undertaking and other Documents to Division Office by the Lowest Tenderer. | To be submitted during office hours within a week from the date of opening of Financial Bid. In case the last day happens to be closed holiday, these documents shall be Submitted on the Next working day.
(i) | Letter of Transmittal Duly signed as given in Annexure-III
(ii) | Copy of receipt for deposition of original EMD (as given in Annexure - I) issued from division office of any Executive Engineer, CPWD. (Including NIT issuing EE/AE, CPWD) deposited in the form of lnsurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt, Banker's Cheque or Bank Guarantee (For balance amount as prescribed) issued by a Commercial Bank against EMD (Bank Guarantee Format as given in Annxure-II).
(iii) | Scan copy of the original EMD
(iv) | CPWD Enlistment order of contractor wherever required as a proof of validity (This is required only for who is registered in CPWD).
(v) | Permanent Account Number (PAN) Card as issued by the Income Tax Department.
(vi) | GST RegistrationCertificate, if already obtained by the bidder. If the bidder has not obtained GST registration as applicable, then such a case bidder shall furnish undertaking as given in Annxure- IV
(vii) | Financial information as given in Form-A
(viii) | Banker's certificate as given in Form-B OR Net worth Certificate issued by certified Chartered Accountants as given in Form-B1
(ix) | Details of eligible similar nature of works completed during the last seven years ending on the last day of the month previous to one in which bids are invited as given in Form-C
(x) | Details of Project Under Execution as given Form 'C-1'
(xi) | Declaration of bidding capacity detail as given Form 'C-3'
(xii) | Performance report of works as given in Form-D
(xiii) | Structure & Organization as given in Form-E
(xiv) | Copy of valid electrical license. The contractors shall be allowed to participate in tender with an undertaking that they will either obtain valid electrical license at the time of execution of electrical work or associates contractors having valid electrical license of eligible class.
(xv) | Undertaking by contractor on his Letter-Head in the following format: "I/We Declare that, I/We have not been Debarred/Blacklisted by Central Government/State Government."
(xvi) | Undertaking by Contractor on his letter head in the following format: "In case, I/We become first lowest tenderer and I/We are not eligible agency as per eligibility criteria; I/We will associate eligible agency fulfilling eligibility criteria as per NIT and I/We will submit documents as required."
(xvii) | ERP training certificate issued through LMS of ERP.
SECTION-II GENERAL CONDITIONS FOR SPECIALIZED ELIGIBLE AGENCIES — pages: 20, 21, 22
No. | Text
1. | "Name of Work: - \"RMO Fire Alarm & Fire Fighting System at Rashtrapati Bhavan, New Delhi. (SH: - Operation & Comprehensive maintenance of Fire Alarm system & Fire Fighting System at different locations in Rashtrapati Bhavan).\"
2. | The tenderer should either himself meet the eligibility criteria for execution of specialized component of work or otherwise he will have to associate with agencies, fulfilling the eligibility requirements prescribed in the tender document.
3. | The tenderer or associateagency shall submit the similar work experience documents in respect of experience of having satisfactory completed similar works as defined below during last seven years ending last day of the month previous to the one in which tenders are invited, issued by client department clearly indicating; 1. Name of Work, 2. Scope of Work, 3. Agreement No., 4. Estimated Cost, 5. Tendered Cost, 6. Final Value of Work Done, 7. Date of Start, 8. Stipulated date of Completion, 9. Actual date of completion, 10. Nature of the Work. (In case some of above said details are not mentioned in the Completion certificate, the firm shall attach sample proof in support of above details), self-attested copy of valid Electrical contractor license, GST registration of the proposed associated specialized agencies for verification (if required) and for approval of the department as per eligibility requirement mentioned in above as per FORM-II within 7(Seven) days from date of issue of Letter of Intent (LOI). Main contractor shall also be required to furnish either copy of applicable licenses/registrations or proof of applying for obtaining labour licenses, registration with EPFO, ESIC and BOCW Welfare Board of proposed associated specialized agencies along with above documents.
4. | Consent letter of such selected associated specialized agencies for association shall also be enclosed in the prescribed format as per FORM-I within 7(Seven) days along with documents.
5. | After approval of associated specialized agencies by Engineer-in-Charge, the main contractor will submit MOU signed with the Associated Specialized Agency as per FORM-III in shape of affidavit on stamp paper duly attested by notary in original within 3 (Three) Days after issue of approval letter (for Associate Specialized Agency). The MoU shall be signed by both the parties i.e. Main Contractor as 1st party and Associated Specialized Agency as 2nd party, independently for all specialized work(s).
Table: Section-II General Conditions for Specialized Eligible Agencies (Parsed Table)
SECTION-II GENERAL CONDITIONS FOR SPECIALIZED ELIGIBLE AGENCIES
Name of Work: - "RMO Fire Alarm & Fire Fighting System at Rashtrapati Bhavan, New Delhi. (SH: - Operation & Comprehensive maintenance of Fire Alarm system & Fire Fighting System at different locations in Rashtrapati Bhavan)."
The tenderer should either himself meet the eligibility criteria for execution of specialized component of work or otherwise he will have to associate with agencies, fulfilling the eligibility requirements prescribed in the tender document.
1. The tenderer shall also be eligible to carry out himself any or all of the above specialized works without associating any specialized agency provided they fulfil the prescribed eligibility criteria for each of the above specialized work(s).In case the main contractor himself is not eligible (as per eligibility criteria) for executing any of the components of E&M work, he can directly associate the OEM/ authorized service provider of the OEM or specialized agency as per criteria mentioned for associate eligible agency. (Joint ventures are not accepted), within 7 days of issue of letter of intent/Acceptance and also after taking prior approval from the Engineer-in-charge.
2. The intending bidder shall upload an undertaking along with the bid that "I/We shall associate specialized agencies as per the above eligibility criteria within 7 days of issue of letter of intent/Acceptance otherwise department may take action against me/us as per clause-3 of the applicable GCC of the agreement & may forfeit performance guarantee absolutely and also shall fulfil all the formalities for association of the specialized agencies as per the conditions mentioned in the \" General conditions for specialized eligible agencies\".
3. The tenderer or associateagency shall submit the similar work experience documents in respect of experience of having satisfactory completed similar works as defined below during last seven years ending last day of the month previous to one in which tenders are invited, issued by client department clearly indicating; 1. Name of Work, 2. Scope of Work, 3. Agreement No., 4. Estimated Cost, 5. Tendered Cost, 6. Final Value of Work Done, 7. Date of Start, 8. Stipulated date of Completion, 9. Actual date of completion, 10. Nature of the Work. (In case some of above said details are not mentioned in the Completion certificate, the firm shall attach sample proof in support of above details), self-attested copy of valid Electrical contractor license, GST registration of the proposed associated specialized agencies for verification (if required) and for approval of the department as per eligibility requirement mentioned in above as per FORM-II within 7(Seven) days from date of issue of Letter of Intent (LOI). Main contractor shall also be required to furnish either copy of applicable licenses/registrations or proof of applying for obtaining labour licenses, registration with EPFO, ESIC and BOCW Welfare Board of proposed associated specialized agencies along with above documents.
4. Consent letter of such selected associated specialized agencies for association shall also be enclosed in the prescribed format as per FORM-I within 7(Seven) days along with documents.
5. | After approval of associated specialized agencies by Engineer-in-Charge, the main contractor will submit MOU signed with the Associated Specialized Agency as per FORM-III in shape of affidavit on stamp paper duly attested by notary in original within 3 (Three) Days after issue of approval letter (for Associate Specialized Agency). The MoU shall be signed by both the parties i.e. Main Contractor as 1st party and Associated Specialized Agency as 2nd party, independently for all specialized work(s).
GENERAL TERMS AND CONDITIONS — pages: 41, 42, 43, 44, 45, 46, 47
No. | Text
1. | Before award of work, contractor is bound to submit the following details of workers proposed to be engaged by him along with PG, failing which the tender may be cancelled and the agency will not be allowed to re-participate for the above work. It is to be noted that PG will not be accepted without the following details: -
2. | The contractor is instructed to submit the verification form for the labour to be deployed by him during course of execution of work in Rashtrapati Bhawan. The verification form can be obtained from the O/o DCP/Sec (RB) and / or concerned JE (E). No labour will be changed without written approval of Engineer-in-charge. If any changes have been done without written approval, then no payment will be released for the changed labour.
3. | The work shall be carried out at Rashtrapati Bhawan, New Delhi, the contractor is advised to quote his rates accordingly.
4. | Contractor is advised to visit the site & check and go through all equipment's mentioned in Schedule of Work / Inventory / Terms & Conditions and also confirm the prevailing market rates before quoting the tender. Nothing shall be paid by Department on account of repairing / replacement of faulty & non working switch gear / component during the handover of site.
5. | The rates quoted shall be inclusive of all Taxes and duties, nothing extra shall be paid on this Account.
6. | If any item is to be different than whatever mentioned in the schedule of work it should specifically be brought out to the notice of department while quoting for the tender.
7. | No T & P shall be issued by the department.
8. | Staff provided for duty shall be professionally competent and experienced to handle the eventualities of electrical installations.
9. | The staff deputed in the work shall be contractor's liability, therefore no claim for continuous or regular employment with the department.
10. | The agency should pay minimum salary per month including ESIC & EPFO in the bank account of employees only and bank statement of the same should be submitted along with bill as a proof of payment to the employee.
11. | Wages shall be payable on the basis of actual number of working days in a month and all the workers will be eligible for one weekly off during the period of employment.
12. | Staff shall be deployed for all days in a week of the month including Gazetted Holidays and National Holidays or any days of holiday. Substitute worker for the rest day and holidays shall be responsibility of the contractor and no extra claim in this regard will be entertained by the department. The quoted rates shall be inclusive of the cost of reliever for any staff. Hence service provider shall provide a reliever for any staff (whenever needed) and nothing extra shall be payable on this account.
13. | All tradesmen shall be appropriately skilled to carry out their trade related works. In case no relevant trade job is available for a particular tradesman / worker during any working hour, his services may be utilized for assisting other tradesman/ or any other maintenance related job may be assigned as per the directions of Engineer-in-charge, No extra claim shall be entertained by the department on this account.
14. | The contractor shall furnish Name & Contract Number and a valid email ID of the Firm and person, who should be contracted during general/emergency contact/complaint emergency.
15. | No extra payment payable for wastage of labour.
16. | Agency has to maintain the logbook & enter all complaint & work done at site and also maintain attendance register duly verified by JE / AE every day.
17. | The operation work is being on contract in absence of permanent Technician, Operator & Khallasi, in case of deputing permanent employee by the department, the contract shall be terminated in between with a prior notice of 15 days to the contractor. In such case the payment shall be made pro-data for work done.
18. | All the dismantled material if any received from site shall be returned to the department and deposited in the store of the JE(E), President Estate for which nothing extra shall be paid.
19. | Department shall in no way be involved in any dispute of whatever kind, between the contractor and the staff engaged by him.
20. | No staff shall leave his duty unless relieved by his relievers. Engineer in charge reserves the right to detain the staff for next shift if the reliever fails to turn up. The O.T.A applicable in this case shall be borne by the contractor.
21. | The cleaning/comprehensive maintenance of system included in the list of Inventory shall be done in accordance with frequency of work, if not done necessary recovery shall be made from the bills of the contractor for which contractor shall be responsible. The recovery amount decided by the Engineer-in-charge salary final and binding on the contractor and this will not be arbitrable.
22. | Any loss or damage to the inventory (as per NIT) by way of theft sabotage or mal-operation of equipment, switch gears shall be made good by the contractor.
23. | Staff shall wear the uniform/dress as per the instruction of Engineer-in-Charge during duty hours at Rashtrapati Bhawan. If any of the staff found without/dress then recovery shall be made @200/- each per day from the contractor's bill.
24. | Site is located in sensitive and high security & VVIP area, where movement and routes are restricted. Some restrictions may be imposed by the Security Agency on the working and for movement of labour, materials etc. The movement of trucks and vehicles shall be regulated in accordance with rules and regulations as approved by competent authority. The contractor shall be bound to follow all such restrictions/instructions and nothing extra shall be payable on this account. No claim whatsoever will be entertained by the department on account of any, restrictions (including temporary suspension of work) imposed by the security agencies in execution of work.
25. | There may be some restrictions on free movement of laborers at site and restriction of working hours and the agency shall consider this fact while quoting the rates and executing the work. Photo passes if any required for worker shall be responsibility of the contractor.
26. | The personal deployed at site should be well behaved having good integrity and shall follow the security protocols of Rashtrapati Bhavan. The personals found misbehaved or of doubtful integrity shall be immediately removed this site and his entry shall be banned. The contractor shall take all precautions while deploying manpower and provide suitable manpower immediately occurrence of such incidents in writing by Engineer-in-charge at his own cost.
27. | The Contractor has to maintain record of all visits and inspection made by staff in a register and shall submit to Engineer-in-charge at every running account bill.
28. | Log book as per standard Performa will have to be filled in by the contractor's staff. The log book shall be kept in the plant room which will be checked by the Engineer - in - charge or his authorized representative. The contractor's staff shall have to take action as per directions of Engineer - in - charge from time to time. The log book shall be supplied by the contractor free of cost as per standard Performa given by the department.
29. | If any staff is on leave, the contractor shall arrange suitable substitute staff.
30. | In case of absence of any staff, recovery at double of the minimum wages of that time shall be made from the contractor's bill.
31. | If break down occurred due to negligence of the contractor's staff, than contractor shall have to replace / repair defective/unserviceable parts/equipment within his quoted rates. Nothing extra shall be paid by the department. If beyond reasonable delay in replacement of parts, then recovery shall be made from the bill as assessed by the Engineer in Charge.
32. | No labour huts shall be allowed inside the campus of above said work. The contractor shall make his own arrangement for the stay of labour outside the campus including transportation and nothing extra shall be payable on this account.
33. | The Contractor shall also be required to follow the rules & restrictions imposed on working/movement/stacking of materials by the local competent authority at all times. Nothing extra shall be payable on this account.
34. | All the materials which are intended to be used in the work shall be got approved from the Engineer-in- Charge before put to work.
35. | The watch and ward of the materials issued to the Contractor or installed at site shall be responsibility of the Contractor till the installations on completion are finally handed over to the Department.
36. | Income Tax, GST and Labour Welfare cess will be deducted at prevailing rates from gross amount of contractor bills.
37. | All the cleaning material i.e. soap, duster etc. shall be arranged by the contractor at his own cost. If cleaning of installation is found unsatisfactory at any time, a recovery of Rs. 200/- per occasion shall be made.
38. | The contractor shall carryout the work at his own responsibility and risk. In case of any accident no claim hall be given to the contractor or his employee by the department.
39. | The staff deputed in the work shall be contractor's liability, therefore no claim for continuous or regular employment with the department.
40. | The contractor shall replace the staff, in the event of misconduct by him.
41. | The department shall not provide any store accommodation for the stores brought by the contractor or issued by the department.
42. | Damage to the building during execution of work shall be made good by the contractor matching with the surrounding surface, otherwise the same shall be got done at the cost of working contractor.
43. | Any damage done to the existing installations by contractor's staff shall be replaced by the contractor at his own cost and risk, to the entire satisfaction of the Engineer-in- Charge.
44. | The makes of material will be as per attached list of approved makes against each item of work or as per instructions of Engineer in charge.
45. | Contractor shall be responsible for conduct of staff/workers deployed at site of work.
46. | The execution of the job shall be done in a workman like manner to give structurally sound and neat appearance.
47. | The work shall be carried out in highly security area hence labour is to be engaged as per availability of site, no claim for idle labour will be accepted.
48. | The contractor shall take all precautions for safety of the workman. If any accident/mishap occur, the department shall not be responsible for the same. Consequently, any compensation payable shall be at the contractor's cost.
49. | Any malba generated due to dismantling/execution shall be cleared from the site of work immediately without any extra cost failing which same shall be done by the department and suitable recovery shall be made form the bill of the bill of the contractor.
50. | The entry of labour/workers and materials into the Rashtrapati Bhawan / President Estate is through temporarily working passes by Security of Rashtrapati Bhawan and DCP Traffic Police for which contractor has to submit the details as required for issue of passes. Any type of losses due to delay and non-issue of passes/permit shall not be the responsibility of department. No claim whatever due to the above aspects shall be entertained by the department.
51. | Strictly no electronic gadget like microphone, mobile phone, pen drive, camera, chip, SIM or other electronic equipment is not allowed in Rashtrapati Bhawan.
52. | Any misbehavior, impersonation & security breaches caused by the labour will not be tolerable at all. The contractor shall be fully responsible for such acts of omission if any legal action is initiated by the competent authority for violating the security measures.
53. | The agency has to provide the warranty for repair and replacement of product for minimum 12 months.
54. | After the expiry of the contract, system will be handed over back to the department's authorized representative with all systems and equipments in 100% functional condition & with complete inventory including as updated during the currency of contract, failing which recovery will be made from contractor's final bill. The decision of Engineer in charge shall be final and binding.
Clause 1
(i)Time allowed for submission of Performance Guarantee, Programme chart (time and progress) and applicable labour licenses, registration with EPFO, ESIC, action Plan for Green Rating Certification, BOCW Welfare Board or proof of applying thereof from the date of issue of letter of acceptance. |  | 7 Days
(ii) Maximum allowable extension with late fee at 0.1% per day of performance guarantee amount beyond the period provided in (i) above |  | 3 Days
Clause 2
Authority for fixing compensation under clause 2 |  | Superintending Engineer, President Estate Circle, New Delhi- 110004
Clause 2A
Whether Clause 2A shall be applicable |  | Not Applicable
Clause 5
Number of days from the date of issue of letter of acceptance for reckoning date of start |  | 7 days after Letter of Acceptance (LOA) or from the date of hand over of site whichever is later.
Table of Milestone
S.No. | Physical / Financial Progress |  | Time allowed (from date of start) | Amount to be withheld in case of non achievement of milestone.
Time allowed for execution of work from date of start | 12 Months
Authority to decide:
(i) Extension of time | EE(E), President Estate Electrical Division, CPWD, New Delhi-110004
(ii) Rescheduling of milestones | Superintending Engineer, President Estate Circle, New Delhi-110004
(iii) Shifting of date of start in case of delay in handing over of site | Superintending Engineer, President Estate Circle, New Delhi-110004
Clause 5A | Not Applicable
Clause 6 | EMB
Clause 7
Gross work to be done together with Net payment / adjustment of advances for material collected, if any, since the last such payment for being eligible to interim payment | Rs.5 Lakh part there of as decided by Engineer-in-Charge.
Clause 7A No Runing Account Bill shall be paid for the work till the applicable labour licenses, Registration with EPFO, ESIC and BOCW Welfare Board, whatever applicable are submittedby the contractor to the Engineer-in-charge. Whether Clause 7A shall be applicable | Applicable
Clause 8A Authority to decide compensation on account if contractor fails to submit completion plans, As built drawings, Services drawing, Standard Measurement Book and Other documents specified in NIT. | Engineer-in-Charge
Clause 10A List of testing equipments to be provided by the contractor at site | As per CPWD Specification
Clause 10C Components of labour expressed as percent of value of work: | Applicable
Clause 10CA | Not Applicable
Clause 10CC Clause 10CC to be applicable in contracts with stipulated period of completion exceeding the period shown in Next column | Not Applicable
Schedule of component of other Materials, Labour etc. For price escalation. Component of Electrical Construction value of work: Xm 50% Component of Labour expressed as percent of total value of work-Y 25%
Clause 11
Specifications to be followed for execution of work | All CPWD General specification for electrical Works with correction slips issued upto last day of receipt of Bids.
Note: | Order of precedence shall be following: (i) Description of Schedule of Quantities. (ii) Particular Specification and Special Condition, if any. (iii) Drawings. (iv) CPWD Specifications. (v) Indian Standard Specifications of B.I.S. (vi)Manufacturer's specifications and as decided by the Engineer-in-Charge. (vii)Sound Engineering practices or well established local construction practices. :unselected: :unselected: :selected:
Clause 12
Type of work | Maintenance Work
12.2. & 12.3 Deviation limit beyond which clauses 12.2 & 12.3 shall apply for building work. For all items of the work | No Limit
(All the deviated quantities shall be paid at agreement rates)
Clause 16 Competent authority for deciding reduced rates. | Superintending Engineer, PEC, New Delhi
Clause 18 List of mandatory machiNery, tools & plants to be deployed by the contractor at site | As per CPWD Specification
Clause 19 C | Engineer-in- Charge
Clause 19 D | Engineer-in- Charge
Clause 19 G | Engineer-in- Charge
Clause 19 K :selected: | Engineer-in- Charge
Clause 25 | Settlement of disputes by Conciliation and Arbitration
Concilator for Conciliation of dispute | Additional. Director General, CPWD, Delhi Region
Arbitrator appointing Authority | Superintendinig Engineer, PEC, CPWD
Place of Arbitration | New Delhi
Clause 31 | Yes Applicable
Requirement of technical representative(s) and recovery rate
Minimum Qualification of Technical Representative | Designation of Technical Staff | Minimum experience (Years) | Number (of major + minor component) | Rate at which recovery shall be made from the contractor in the event of not fulfilling provision of clause 32
|  |  |  | Figures | Word
Graduate Engineer Or Diploma Engineer (Electrical) | Project Manager Cum planning / Quality/site /billing Engineer | 2 Years Or 5 Years respectively | 1 | Rs.15,000/- Per month | Rupees Fifteen Thousand per Month.
S.No. | Name of worker/ Employee | Category | Address | Qualification & Experience in case of skilled Worker | Adhar No. (Photo to enclosed) | Card copy be | Workers/Employee Bank Details i.e. A/c No., Bank & Branch (Copy of Cancelled Cheque/ photocopy of passbook to be enclosed)
Special Conditions for maintenance tenders — pages: 49, 50
No. | Text
1. | All the workers should wear proper dress i.e. Light Blue Color Shirt Full Sleeve and Navy Blue Trousers along with Leather Safety Shoe. If a worker is found without proer dress then a penalty of Rs 1000/- per case will be imposed by the deptt and will be deducted from next month bill.
2. | Worker will display his name and designation along with subdivision and division name and lastly CPWD logo. His shirt should display CPWD logo on the back. Logo should be of thread knitting.
3. | Contractor has to design a carry suitcase (with / without trolly) which should be capable of arranging all the necessary equipment in that suitcase AND SHOULD BE APPROVED BY THE ENGINEER IN CHARGE.
4. | All the workers should be preferably below 50 years and maximum 10% of the work force can be of age more than 50 years.
5. | The contractor has to submit the details of the work executed by each workman in the form of two photos i.e. before and after attending the complaint. The contractor has to employ Computer Operator for arranging all these photographs in a daily folder and monthly folder to be submitted in the form Pen-Drive to the AE concerned.
6. | All the workers will come at the designated place in the morning 5 minute before the working hours and the contractor will take GI Tag photograph and submit the attendance in terms of numbers present / total number as per tender. Same exercise has to be completed just 5 minutes before closing time of working hours both the photograph will be submitted to JE concerned to the respective section.
7. | If a worker found a absent without prior replacement, then a penalty of 3 times of the daily wages as per the minimum wages act will be imposed.
8. | If a worker is being replaced with prior approval, then he should come in proper dress as described as Para No. 1 & 2 and he should have qualification either more or equal to the qualification of earlier workmen.
9. | It is presumed that contractor will make all the payments due to the workman through banks and if any complain of forced demand of money by the contractor or his representative is received from the workman and if contractor is found guilty then the necessary criminal case will be filed against the contractor and the firm will be banned at least for 05 years and his name will be recommended to the directorate to be banned for lifetime.
10. | If the satisfaction level is reported by the resident as below good or not satisfactory then contractor will be given a chance to correct the mistake but even after the 2nd attempt the response is not satisfactory then a penalty of Rs. 5,000/- will be imposed for each such unsatisfactory work.
11. | A performance appraisal form will be prepared by the department and the contractor will make a google link for the appraisal form and JE will ensure that the non-editable responses will be kept on record for at least 20 residents/ officers per inquiry and if contractor fails to get average less than 8.0 on a scale of 1 to 10 then he will be given a chance for another month to improve and if the contractor fails to improve the rating then his work will be terminated without any notice. For continuation of the work, one month time will be given to the contractor to bind up and the department to call new tender and put the agency in place. Such contractors will be debarred for 3 years for participating in such tender.
12. | The contractor has to keep an eye on the balance stock of the material required for the satisfactory maintenance of the asset for which he / she has been given the job and he must order the additional stock after getting necessary approval from competent authority, if the current stock has reached to the threshold level. The purpose of this clause to maintain always a minimum balance of material in the stock.
13. | The contractor will follow all the statutory provisions, guidelines, law and any other orders being issued by the Govt. from time to time and he / she will ensure that all the necessary payments and facilities are being provided as per the Govt. orders.
14. | Contractor should brief all the workmen everyday morning about the security and safety protocol and also about the polite behavior which a worker is suppose to do with residence / officer.
15. | If a worker is found to be chewing Gutakha, Tabacco, Paan etc. or having liquor etc. or smoking then a penalty of Rs. 5,000/- will be imposed per incident and the worker will be removed.
Maintenance of Fire-Fighting System — pages: 61, 62, 63
No. | Text
1. | The firm shall submit an undertaking that they shall deploy licensed personal as required under IE Act & carry out work on Electrical panel and related Electrical works.
2. | The nature of job is very highly skilled, so the contractor has to employ highly skilled technicians/engineer for fortnightly visit/ As and when required to the system who must be well experienced in the field of Fire - Fighting system. (i) In case the contractor fail to maintained the system properly a recovery @ Rs. 5000/- per event or day shall be recovered from him. (ii) In case of non-carrying out preventive maintenance as per schedule recovery will be made from the bill of contractor @ Rs. 2000/- each per day or occasion.
3. | The department reserves the right to check control room and connected equipment for this completeness and performance as and when required. It will be responsibility of the contractor to keep the system clean and in order.
4. | The contractor shall take all precaution as per requirement of I-E rule & regulation 1959. The contractor shall be liable to pay compensation to the staff engaged by him in such cases in the event of any accident.
5. | In case of performance of work is found unsatisfactory, the Engineer-in-Charge may terminate the contract without any notice and no claim shall be allowed after the termination of contract.
6. | The technicians are required to be reported to the Engineer-In charge at scheduled time of his/her duty to ensure the smooth working of all the Fire Fighting system equipment's or as per the instructions from Engineer in-Charge.
7. | Scope of the work for the contractor shall be as follows: - a) Cleaning/overhauling and servicing of all equipment's, performing the daily/weekly/monthly/six monthly checks as per manufacturer recommendations/ CPWD specification or as per direction of engineer-in- charge. b) The Control Room shall be managed round the clock by the contractor. In case of Fire Fighting System & gas flooding system, Remarks and observations regarding maintenance / malfunctioning of Fire Fighting system & Panel & allied services, Gas flooding system and allied accessories recorded in the log book / conveyed through message / letter shall be attended within 24 hrs. c) In above system if contractors fails, same shall be got rectified by the department at the risk and cost of the firm without entering into any correspondence and necessary recovery shall be made from the bill of the contractor. The necessary consumable materials & tool items for maintaining the system shall be arranged by the firm at their own cost and shall be kept ready at site in sufficient quantity under the scope of work for which nothing extra shall be paid. d) The staff deployed by the bidder shall carry out rectification works wherever necessary for proper and reliable operation of the Fire Fighting installation. e) Repair and replacement of flow switch, air release valve, hose reels, hose drums, hose pipes, coupling, hose cabinet & associated addressable control panel & fire accessories etc. f) Checking of all Fire Extinguishers provided at various locations for their serviceability w.r.t leakage, thorough cleaning, due date record, safety seal check, nozzle and hose pipe, hose reel, hose cabinets lock checks to keep the entire system in ready to operate state once in a quarter period. Re- filling of the fire extinguisher as per standard norms/ due date will be cover under the comprehensive maintenance and at no extra cost paid by department. g) In case of an emergency hour, the agency will have to attend/rectify the same for which no additional payment will be made by the department. h) The firms must have to maintain one First Aid Kit Box with the required medicine etc., which is to be verified by the Engineer-in-Charge or his authorized representatives on a regular basis, failing which, penal recovery @ Rs 100/-per person per month will be made from bills. i) In the event of any accident during the operation or maintenance of the equipment leading to injuries, damage to human beings, equipment, or loss of life, the contractor shall be fully responsible for the setting claims and indemnities. In this respect, no compensation shall be made by the department. j) All installations shall be kept clean and safe from the risk of fire, theft, accidents, damage etc. k) The contractor will keep the department indemnified against all losses, damage or liability arising out of or imposed in the context of the staff employment by him. l) It shall be entirely the responsibility of the contractor to ensure that no unlawful act is done by his personnel while on duty. In case any theft or loss of department property takes place due to the negligence or carelessness of his personnel, the contractor will be held responsible and shall make good the same.

## Acceptable Make
Acceptable Make — pages: 14, 15, 16
No. | Text
Notifier
Bosch
Edward

## Documents to Upload
List of Documents to be scanned and uploaded within the period of bid submission — pages: 8
No. | Text
(i) | Letter of Transmittal Duly signed as given in Annexure-III
(ii) | Copy of receipt for deposition of original EMD (as given in Annexure - I) issued from division office of any Executive Engineer, CPWD. (Including NIT issuing EE/AE, CPWD) deposited in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt, Banker's Cheque or Bank Guarantee (For balance amount as prescribed) issued by a Commercial Bank against EMD (Bank Guarantee Format as given in Annxure-II).
(iii) | Scan copy of the original EMD
(iv) | CPWD Enlistment order of contractor wherever required as a proof of validity (This is required only for who is registered in CPWD).
(v) | Permanent Account Number (PAN) Card as issued by the Income Tax Department.
(vi) | GST RegistrationCertificate, if already obtained by the bidder. If the bidder has not obtained GST registration as applicable, then such a case bidder shall furnish undertaking as given in Annxure- IV
(vii) | Financial information as given in Form-A
(viii) | Banker's certificate as given in Form-B OR Net worth Certificate issued by certified Chartered Accountants as given in Form-B1
(ix) | Details of eligible similar nature of works completed during the last seven years ending on the last day of the month previous to one in which bids are invited as given in Form-C
(x) | Details of Project Under Execution as given Form 'C-1'
(xi) | Declaration of bidding capacity detail as given Form 'C-3'
(xii) | Performance report of works as given in Form-D
(xiii) | Structure & Organization as given in Form-E
(xiv) | Copy of valid electrical license. The contractors shall be allowed to participate in tender with an undertaking that they will either obtain valid electrical license at the time of execution of electrical work or associates contractors having valid electrical license of eligible class.
(xv) | Undertaking by contractor on his Letter-Head in the following format: "I/We Declare that, I/We have not been Debarred/Blacklisted by Central Government/State Government."
(xvi) | Undertaking by Contractor on his letter head in the following format: "In case, I/We become first lowest tenderer and I/We are not eligible agency as per eligibility criteria; I/We will associate eligible agency fulfilling eligibility criteria as per NIT and I/We will submit documents as required."
(xvii) | ERP training certificate issued through LMS of ERP.
Notes
* | a) The Postal address of Executive Engineer (E), President Estate Electrical Division, CPWD may be noted as below for correspondence and submission of Physical documents. O/o The Executive Engineer (E), President Estate Electrical Division, CPWD, South Basement, Rashtrapati Bhavan, New Delhi-110004.
* | b) List of documents mentioned in point vii, viii, x, & xiii are not applicable for CPWD enlisted contractors of appropriate class and serial no. iv is not applicable for Non-CPWD Contractor / OEM. Therefore, Agencies shall upload separate letters that these documents are not required to be submitted by them. Uploading of these letters is mandatory otherwise system will not clear the mandatory fields.
* | c) Additional following Mandatory Documents has to be submitted alongwith Performance Guarantee by the lowest tenderer failing which EMD shall be forfeited without further intimation.
* | i. Willingness Certificate from Notifier Make (Authorized to work in New Delhi area) as per Page - 14.
* | ii. Willingness Certificate from Bosch Make (Authorized to work in New Delhi area) as per Page - 15.
* | iii. Willingness Certificate from Edward Make (Authorized to work in New Delhi area) as per Page - 16.

## Schedule of Quantity
SCHEDULE OF QUANTITY — pages: 66
Sl.No. | Bhavan). Description of Items | Qty |  | Rate | Unit | Amount
1 | Running, Operation and Routine Maintenance of fire fighting and sprinkler system by deputing the staff as per inventory, terms and conditions attached etc. complete as required. | 12.00 | Month | 162920.00 | Per Month | 19,55,040.00
2 | Running, Operation and Routine Maintenance of fire Alarm system by deputing the staff as per inventory, terms and conditions attached etc. complete as required. | 12.00 | Month | 235308.00 | Per Month | 28,23,696.00
3 | Annual comprehensive maintenance of following intelligent addressable fire alarm/ detection & PA system installed at Main building i/c Major/Minor repairing & replacement of all defective detectors, wiring & other accessories etc with upkeep & cleaning the panels, detectors and its accessories complete (Inventory attached) as per terms & conditions enclosed as reqd.
a) | Intelligent addressable fire alarm system (Bosch, Notifier & Edward) | 12.00 | Month | 90408.00 | Per Month | 10,84,896.00
Grand Total | 58,63,632.00