## Terms and Conditions
Heading in source document: | General Terms & Conditions (pages 44-48 of the NIT)
S.No. | Term / Condition
1 | Before award of work, contractor is bound to submit the following details of workers proposed to be engaged by him along with PG, failing which the tender may be cancelled and the agency will not be allowed to re-participate for the above work. It is to be noted that PG will not be accepted without the following details: -
2 | The contractor is instructed to submit the verification form for the labour to be deployed by him during course of execution of work in Rashtrapati Bhawan. The verification form can be obtained from the O/o DCP/Sec (RB) and / or concerned JE (E). No labour will be changed without written approval of Engineer-in-charge. If any changes have been done without written approval, then no payment will be released for the changed labour.
3 | The work shall be carried out at Rashtrapati Bhawan, New Delhi, the contractor is advised to quote his rates accordingly.
4 | Contractor is advised to visit the site & check and go through all equipment's mentioned in Schedule of Work / Inventory / Terms & Conditions and also confirm the prevailing market rates before quoting the tender. Nothing shall be paid by Department on account of repairing / replacement of faulty & non working switch gear / component during the handover of site.
5 | The rates quoted shall be inclusive of all Taxes and duties, nothing extra shall be paid on this Account.
6 | If any item is to be different than whatever mentioned in the schedule of work it should specifically be brought out to the notice of department while quoting for the tender.
7 | No T & P shall be issued by the department.
8 | Staff provided for duty shall be professionally competent and experienced to handle the eventualities of electrical installations.
9 | The agency should pay minimum salary per month including ESIC & EPFO in the bank account of employees only and bank statement of the same should be submitted along with bill as a proof of payment to the employee.
10 | The firm shall abide Contractor Labour Regulations amended up to date and the payment to staff shall be made (as per Minimum Wages Act. as notified by the Govt. of India) through ECS upto 7th of each month. Beyond 7th of each month failing which the recovery will be made @ of 1% of monthly salary for each worker each day (Skilled / Unskilled). The payment to the contractor will be released only after giving proof to the department for the same with bill duly verified by AE/JE(E).
11 | Wages shall be payable on the basis of actual number of working days in a month and all the workers will be eligible for one weekly off during the period of employment.
12 | Staff shall be deployed for all days in a week of the month including Gazetted Holidays and National Holidays or any days of holiday. Substitute worker for the rest day and holidays shall be responsibility of the contractor and no extra claim in this regard will be entertained by the department. The quoted rates shall be inclusive of the cost of reliever for any staff. Hence service provider shall provide a reliever for any staff (whenever needed) and nothing extra shall be payable on this account.
13 | All tradesmen shall be appropriately skilled to carry out their trade related works. In case no relevant trade job is available for a particular tradesman / worker during any working hour, his services may be utilized for assisting other tradesman/ or any other maintenance related job may be assigned as per the directions of Engineer-in-charge, No extra claim shall be entertained by the department on this account.
14 | The contractor shall furnish Name & Contract Number and a valid email ID of the Firm and person, who should be contracted during general/emergency contact/complaint emergency.
15 | No extra payment payable for wastage of labour.
16 | Agency has to maintain the logbook & enter all complaint & work done at site and also maintain attendance register duly verified by JE / AE every day.
17 | The operation work is being on contract in absence of permanent Technician, Operator & Khallasi, in case of deputing permanent employee by the department, the contract shall be terminated in between with a prior notice of 15 days to the contractor. In such case the payment shall be made pro-data for work done.
18 | All the dismantled material if any received from site shall be returned to the department and deposited in the store of the JE(E), President Estate for which nothing extra shall be paid.
19 | Department shall in no way be involved in any dispute of whatever kind, between the contractor and the staff engaged by him.
20 | No staff shall leave his duty unless relieved by his relievers. Engineer in charge reserves the right to detain the staff for next shift if the reliever fails to turn up. The O.T.A applicable in this case shall be borne by the contractor.
21 | The cleaning/comprehensive maintenance of system included in the list of Inventory shall be done in accordance with frequency of work, if not done necessary recovery shall be made from the bills of the contractor for which contractor shall be responsible. The recovery amount decided by the Engineer-in-charge salary final and binding on the contractor and this will not be arbitrable.
22 | Any loss or damage to the inventory (as per NIT) by way of theft sabotage or mal-operation of equipment, switch gears shall be made good by the contractor.
23 | Staff shall wear the uniform/dress as per the instruction of Engineer-in-Charge during duty hours at Rashtrapati Bhawan. If any of the staff found without/dress then recovery shall be made @200/- each per day from the contractor's bill.
24 | Site is located in sensitive and high security & VVIP area, where movement and routes are restricted. Some restrictions may be imposed by the Security Agency on the working and for movement of labour, materials etc. The movement of trucks and vehicles shall be regulated in accordance with rules and regulations as approved by competent authority. The contractor shall be bound to follow all such restrictions/instructions and nothing extra shall be payable on this account. No claim whatsoever will be entertained by the department on account of any, restrictions (including temporary suspension of work) imposed by the security agencies in execution of work.
25 | There may be some restrictions on free movement of laborers at site and restriction of working hours and the agency shall consider this fact while quoting the rates and executing the work. Photo passes if any required for worker shall be responsibility of the contractor.
26 | The personal deployed at site should be well behaved having good integrity and shall follow the security protocols of Rashtrapati Bhawan. The personals found misbehaved or of doubtful integrity shall be immediately removed this site and his entry shall be banned. The contractor shall take all precautions while deploying manpower and provide suitable manpower immediately occurrence of such incidents in writing by Engineer-in-charge at his own cost.
27 | The Contractor has to maintain record of all visits and inspection made by staff in a register and shall submit to Engineer-in-charge at every running account bill.
28 | Log book as per standard Performa will have to be filled in by the contractor's staff. The log book shall be kept in the plant room which will be checked by the Engineer - in - charge or his authorized representative. The contractor's staff shall have to take action as per directions of Engineer - in - charge from time to time. The log book shall be supplied by the contractor free of cost as per standard Performa given by the department.
29 | If any staff is on leave, the contractor shall arrange suitable substitute staff.
30 | In case of absence of any staff, recovery at double of the minimum wages of that time shall be made from the contractor's bill.
31 | If break down occurred due to negligence of the contractor's staff, than contractor shall have to replace / repair defective/unserviceable parts/equipment within his quoted rates. Nothing extra shall be paid by the department. If beyond reasonable delay in replacement of parts, then recovery shall be made from the bill as assessed by the Engineer in Charge.
32 | No labour huts shall be allowed inside the campus of above said work. The contractor shall make his own arrangement for the stay of labour outside the campus including transportation and nothing extra shall be payable on this account.
33 | The Contractor shall also be required to follow the rules & restrictions imposed on working/movement/stacking of materials by the local competent authority at all times. Nothing extra shall be payable on this account.
34 | All the materials which are intended to be used in the work shall be got approved from the Engineer-in- Charge before put to work.
35 | The watch and ward of the materials issued to the Contractor or installed at site shall be responsibility of the Contractor till the installations on completion are finally handed over to the Department.
36 | Income Tax, GST and Labour Welfare cess will be deducted at prevailing rates from gross amount of contractor bills.
37 | All the cleaning material i.e. soap, duster etc. shall be arranged by the contractor at his own cost. If cleaning of installation is found unsatisfactory at any time, a recovery of Rs. 200/- per occasion shall be made.
38 | The contractor shall carryout the work at his own responsibility and risk. In case of any accident no claim hall be given to the contractor or his employee by the department.
39 | The staff deputed in the work shall be contractor's liability, therefore no claim for continuous or regular employment with the department.
40 | The contractor shall replace the staff, in the event of misconduct by him.
41 | The department shall not provide any store accommodation for the stores brought by the contractor or issued by the department.
42 | Damage to the building during execution of work shall be made good by the contractor matching with the surrounding surface, otherwise the same shall be got done at the cost of working contractor.
43 | Any damage done to the existing installations by contractor's staff shall be replaced by the contractor at his own cost and risk, to the entire satisfaction of the Engineer-in- Charge.
44 | The makes of material will be as per attached list of approved makes against each item of work or as per instructions of Engineer in charge.
45 | Contractor shall be responsible for conduct of staff/workers deployed at site of work.
46 | The execution of the job shall be done in a workman like manner to give structurally sound and neat appearance.
47 | The work shall be carried out in highly security area hence labour is to be engaged as per availability of site, no claim for idle labour will be accepted.
48 | The contractor shall take all precautions for safety of the workman. If any accident/mishap occur, the department shall not be responsible for the same. Consequently, any compensation payable shall be at the contractor's cost.
49 | Any malba generated due to dismantling/execution shall be cleared from the site of work immediately without any extra cost failing which same shall be done by the department and suitable recovery shall be made form the bill of the bill of the contractor.
50 | The entry of labour/workers and materials into the Rashtrapati Bhawan / President Estate is through temporarily working passes by Security of Rashtrapati Bhawan and DCP Traffic Police for which contractor has to submit the details as required for issue of passes. Any type of losses due to delay and non-issue of passes/permit shall not be the responsibility of department. No claim whatever due to the above aspects shall be entertained by the department.
51 | Strictly no electronic gadget like microphone, mobile phone, pen drive, camera, chip, SIM or other electronic equipment is not allowed in Rashtrapati Bhawan.
52 | Any misbehavior, impersonation & security breaches caused by the labour will not be tolerable at all. The contractor shall be fully responsible for such acts of omission if any legal action is initiated by the competent authority for violating the security measures.
53 | The agency has to provide the warranty for repair and replacement of product for minimum 12 months.
54 | After the expiry of the contract, system will be handed over back to the department's authorized representative with all systems and equipments in 100% functional condition & with complete inventory including as updated during the currency of contract, failing which recovery will be made from contractor's final bill. The decision of Engineer in charge shall be final and binding.
Note | Clause 1 is followed in the source document by a blank data-entry table for worker details, with column headers: S.No., Name of worker/Employee, Category, Address, Qualification & Experience in case of skilled Worker, Aadhar No. (Photo to be enclosed), Workers/Employee Bank Details i.e. A/c No., Bank & Branch (Copy of Cancelled Cheque/photocopy of passbook to be enclosed). No data is filled in this table in the source document.

## Acceptable Make
Acceptable Make
Value: | null
Note | No 'Acceptable Make' / 'List of Approved Makes' table is present in the provided pages. Clause 44 of the General Terms & Conditions states: "The makes of material will be as per attached list of approved makes against each item of work or as per instructions of Engineer in charge" — but the referenced list itself (e.g. an Inventory or Schedule of Quantities section, per the document's own index) is not included in the supplied text/pages.

## Documents to Upload
Heading in source document: | List of Documents to be scanned and uploaded within the period of bid submission (page 8 of the NIT)
S.No. | Document
(i) | Letter of Transmittal Duly signed as given in Annexure-III
(ii) | Copy of receipt for deposition of original EMD (as given in Annexure-I) issued from division office of any Executive Engineer, CPWD (Including NIT issuing EE/AE, CPWD) deposited in the form of Insurance Surety Bonds, Account Payee Demand Draft, Fixed Deposit Receipt, Banker's Cheque or Bank Guarantee (For balance amount as prescribed) issued by a Commercial Bank against EMD (Bank Guarantee Format as given in Annexure-II).
(iii) | Scan copy of the original EMD
(iv) | CPWD Enlistment order of contractor wherever required as a proof of validity (This is required only for who is registered in CPWD).
(v) | Permanent Account Number (PAN) Card as issued by the Income Tax Department.
(vi) | GST Registration Certificate, if already obtained by the bidder. If the bidder has not obtained GST registration as applicable, then such a case bidder shall furnish undertaking as given in Annexure-IV
(vii) | Financial information as given in Form-A
(viii) | Banker's certificate as given in Form-B OR Net worth Certificate issued by certified Chartered Accountants as given in Form-B1
(ix) | Details of eligible similar nature of works completed during the last seven years ending on the last day of the month previous to one in which bids are invited as given in Form-C
(x) | Details of Project Under Execution as given Form 'C-1'
(xi) | Declaration of bidding capacity detail as given Form 'C-3'
(xii) | Performance report of works as given in Form-D
(xiii) | Structure & Organization as given in Form-E
(xiv) | Copy of valid electrical license. The contractors shall be allowed to participate in tender with an undertaking that they will either obtain valid electrical license at the time of execution of electrical work or associates contractors having valid electrical license of eligible class.
(xv) | Undertaking by contractor on his Letter-Head in the following format: "I/We Declare that, I/We have not been Debarred/Blacklisted by Central Government/State Government."
(xvi) | Undertaking by Contractor on his letter head in the following format: "In case, I/We become first lowest tenderer and I/We are not eligible agency as per eligibility criteria; I/We will associate eligible agency fulfilling eligibility criteria as per NIT and I/We will submit documents as required."
(xvii) | ERP training certificate issued through LMS of ERP.
Note (a) | The Postal address of Executive Engineer (E), President Estate Electrical Division, CPWD may be noted as below for correspondence and submission of Physical documents: O/o The Executive Engineer (E), President Estate Electrical Division, CPWD, South Basement, Rashtrapati Bhavan, New Delhi-110004.
Note (b) | List of documents mentioned in point vii, viii, x, & xiii are not applicable for CPWD enlisted contractors of appropriate class and serial no. iv is not applicable for Non-CPWD Contractor / OEM. Therefore, Agencies shall upload separate letters that these documents are not required to be submitted by them. Uploading of these letters is mandatory otherwise system will not clear the mandatory fields.
Note (c) | Additional following Mandatory Documents has to be submitted alongwith Performance Guarantee by the lowest tenderer failing which EMD shall be forfeited without further intimation: (i) Willingness Certificate from Notifier Make (Authorized to work in New Delhi area) as per Page-14. (ii) Willingness Certificate from Bosch Make (Authorized to work in New Delhi area) as per Page-15. (iii) Willingness Certificate from Edward Make (Authorized to work in New Delhi area) as per Page-16.